## Stonetree
TORO | Stonetree CC Kileen tx
2025-09-25 | DESCRIPTION # | unit price | QTY | TOTAL |  | RECV'D
0
*
| CENTRAL CONTROL |  | #REF!
NSN-ULTIMATE-L | LYNX CE, LSS, LST, 5Y | NO CHARGE | 1
CS_Opt | CS Optimization (Includes computer set-up & training, initial start up training. | 4500 | 1 | 4500
LSFI-SR | LSFI, Standard Wire + Comm Radio | 3144.38 | 1 | 3144.38
RF_Opt | RF Optimization (Includes Frequency Survey, with new FCC license application) |  | 1 | 0
DE-RSP-1000-M | DEC-RSP-1000-M | 4299.99 | 2 | 8599.98
GT | GROUND TESTING, includes up to 30 ground points w/ 8-hrs. onsite max | 3000 | 1 | 3000
TORO SATELLITE CONTROLLER
LSM-1 | LYNX SMART MODULE, 1 STA | 6947.78 | 1 | 6947.78 |  |  |  | Invoice Recv'd/Cleared
|  | billed $96.53 | billed 2 | billed $193.06
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
*
| TORO VIH ROTORS |  | 345.37 | 0
FLX35-348-2 | SPK,1IN,PC,34N,80P,SG | 260.48 | 192 | 50012.16 |  | 192 |  | Invoice Recv'd/Cleared
FLX35-358-2 | SPK,1IN,PC,35N,80P,SG | 260.48 | 288 | 75018.24 |  | 252 | Short 36 | Invoice Recv'd/Cleared
FLX34-338-2 | SPK,1IN,FC,33N,80P,SG | 244.58 | 736 | 180010.88 |  | 736 |  | Invoice Recv'd/Cleared
FLX34-348-2 | SPK,1IN,FC,34N,80P,SG | 244.58 | 73 | 17854.34 |  | 73 |  | Invoice Recv'd/Cleared
|  | HEADS | 1289
0
SWING JOINTS & SERVICE FITTINGS
| LASCO 1-1/2" ACME INLET x 1-1/4" (12") BODY x 1" ACME TRIPLE-TOP OUTLET SJ | 57.53 | 1315 | 75651.95 |  | 1097 | 218 missing
AFAS150-020 | 2" X 1-1/2" AQUAFUSE SERVICE SADDLE | 29.76 | 1315 | 39134.4 |  | 1315
| 2" cap | 15 | 500 | 7500 |  | 500
| QUICK COUPLING VALVES |  | 173.371
474-44 | QCV 1, LAV VYL CVR W/LK, ACME | 65.84 | 42 | 2765.28 |  | 42 |  | Invoice Recv'd/Cleared
AFAS150-020 | 2" X 1-1/2" AQUAFUSE SERVICE SADDLE | 29.76 | 42 | 1249.92 |  | 42
AF1AS-212 | LASCO 1-1/2" AF INLET x 1" (12") BODY x 1" ACME STANDARD TOP OUTLET SJ | 63.53 | 42 | 2668.26 |  | 42
TVB-6RND-G | BOX,TORO VLV,6X9 ROUND,GREEN | 5.4 | 42 | 226.8 |  | 42 |  | Invoice Recv'd/Cleared
| 1' SCH.40 PVC PIPE | 1 | 84 | 84
QCV KEY & SWIVEL
474-100 | QCV 1, LAV VYL CVR W/LK, ACME | 42.53 | 4 | 170.12 |  | 4 |  | Invoice Recv'd/Cleared
464-03 | SVL HOSE ADP, 1"NPT X .75"MHT | 29.3 | 4 | 117.2 |  | 4 |  | Invoice Recv'd/Cleared
LARGE TURF ACCESSORIES
1.25" Golf Body -Tools & Acc.
995-15 | TOOL, ADJUSTABLE | 7 | 10 | 70 |  | 10 |  | Invoice Recv'd/Cleared
995-83 | UTILITY TOOL | 35.68 | 10 | 356.8 |  | 10 |  | Invoice Recv'd/Cleared
995-100 | PLIER, SNAP-RING, W/SCREEN REMOVER | 128.42 | 5 | 642.1 |  | 5 |  | Invoice Recv'd/Cleared
995-76 | VALVE INSTL TOOL | 199.69 | 4 | 798.76 |  | 4 |  | Invoice Recv'd/Cleared
*
| DR11 PE4710 HDPE PIPE |  | 172753.5
S0200DR110P47BBXX2000 | HDPE PIPE IPS 2 X 2000' DR11 4710 WATER NO STRIPE | 0.68 | 90000 | 61200
S0400DR110P47BBXX0050 | HDPE PIPE IPS 4 X 50' DR11 4710 WATER NO STRIPE | 2.45 | 20000 | 49000 |  | 20000
S0600DR110P47BBXX0050 | HDPE PIPE IPS 6 X 50' DR11 4710 WATER NO STRIPE | 5.3 | 6000 | 31800 |  | 6000
S0800DR110P47BBXX0050 | HDPE PIPE IPS 8 X 50' DR11 4710 WATER NO STRIPE | 8.99 | 2300 | 20677 |  | 2300
S1000DR110P47BBXX0050 | HDPE PIPE IPS 10 X 50' DR11 4710 WATER NO STRIPE | 13.96 | 400 | 5584 |  | 400
S1200DR110P47BBXX0050 | HDPE PIPE IPS 12 X 50' DR11 4710 WATER NO STRIPE | 19.64 | 150 | 2946 |  | 150
S1600DR110P47BBXX0050 | HDPE PIPE IPS 16 X 50' DR11 4710 WATER NO STRIPE | 30.93 | 50 | 1546.5 |  | 50
|  | PIPE | 118900
0
0
| DI IPS GATE VALVE w/ DR11 PE ENDS & OP-NUT |  | 37412.13
| 4" IPS DI GATE VALVE w/ DR11 PE ENDS & OP-NUT | 885.33 | 17 | 15050.61 |  | 17
| 6" IPS DI GATE VALVE w/ DR11 PE ENDS & OP-NUT | 1324.56 | 7 | 9271.92 |  | 7
| 8" IPS DI GATE VALVE w/ DR11 PE ENDS & OP-NUT | 2058.44 | 4 | 8233.76 |  | 4
| 12" IPS DI GATE VALVE w/ DR11 PE ENDS & OP-NUT | 3707.44 | 1 | 3707.44 |  | 1
TVB-10RND-G | BOX,TORO VLV,10X10 ROUND,GREEN | 21.6 | 29 | 626.4 |  | 29
| 8" ADS N-12 CORRUGATED PIPE (SLEEVE) | 6 | 87 | 522
*
| LATERAL ISOLATION VALVES |  | 322.13
AFBV-200Y-MFN0-360 | 2" AQUAFUSE CONTROLFLO 360 BALL VALVE, DR11 PE4710 FULL PORT | 263.53 | 205 | 54023.65 |  | 205
| 2" 90-ELL, S/F DR11 4710 | 6.67 | 205 | 1367.35 |  | 205
| 2" COUPLING, S/F DR11 4710 | 4.11 | 205 | 842.55 |  | 205
70 | 4" X 2" SIDEWALL BRANCH SADDLE, B/F DR11 | 14.44 | 117 | 1689.48 |  | 117
179 | 6" X 2" SIDEWALL BRANCH SADDLE, B/F DR11 | 14.44 | 71 | 1025.24 |  | 71
24 | 8" X 2" SIDEWALL BRANCH SADDLE, B/F DR11 | 14.44 | 15 | 216.6 |  | 15
99 | 12" X 2" SIDEWALL BRANCH SADDLE, B/F DR11 | 14.44 | 2 | 28.88 |  | 2
TVB-10RND-G | BOX,TORO VLV,10X10 ROUND,GREEN | 21.6 | 205 | 4428 |  | 205
| CHRISTY #IC.MAX.P2.RC006 RECLAIMED WATER TAG | 7.34 | 205 | 1504.7
| 6" ADS N-12 CORRUGATED PIPE (SLEEVE) | 4.44 | 205 | 910.2
| PRESSURE REGULATING VALVE (6" w/ 2" BY-PASS) |  | #DIV/0!
| CONCRETE VAULT |  |  | 0
| 6" CLA-VAL #694G-25BCSYKCX D/S CL150FL |  |  | 0
| 2" CLA-VAL #694G-25BCSYKCX D/S CL150FL |  | 0 | 0
| 8" X 6" DI REDUCER (FLG. x FLG.) |  | 0 | 0
| 8" X 2" DI REDUCING TEE (FLG. x FLG.) |  | 0 | 0
| 6" CLOW DI RW GATE VALVE w/ OP-NUT (FLG. X FLG.) |  | 0 | 0
| 2" NIBCO T-113 IRR-BHW GATE VALVE |  | 0 | 0
| 6" X 60" DI FLANGED SPOOL |  | 0 | 0
| 6" X 36" DI FLANGED SPOOL |  | 0 | 0
| 2" DI THREADED ADAPTER, (FLG. X FNPT) |  | 0 | 0
| 2" X 4" DI NIPPLE, TBE |  | 0 | 0
| 2" DI 90-ELL, TBE FNPT |  | 0 | 0
| 2" X 24" DI NIPPLE, TBE |  | 0 | 0
| 2" X 3" DI NIPPLE, TBE (4 per) |  | 0 | 0
| 2" DI UNION, THREADED |  | 0 | 0
| 8" HDPE X FLANGE ADAPTER |  | 0 | 0
| 8" BACKUP RING |  | 0 | 0
| 8" FLANGE NBG KIT |  | 0 | 0
312BC | NDS 10" ROUND VALVE BOX w/ LID, GREEN |  | 0 | 0
| CHRISTY #IC.MAX.P2.RC006 RECLAIMED WATER TAG |  | 0 | 0
| 6" ADS N-12 CORRUGATED PIPE (SLEEVE) |  | 0 | 0
| 3/4" CRUSHED GRAVEL SUMP (2 cu.ft.) |  | 0 | 0
| BRICKS |  | 0 | 0
| AIR RELIEF VALVES |  | 937.83
PL10A | 2" CRISPIN PL10A AIR/VACUUM RELEASE VALVE | 573.41 | 5 | 2867.05 |  | 5
AFBV-200Y-MFNO-000 | AQUAFUSE 2" PE X PE 1/4 TURN FULL PORT BALL VALVE | 161.25 | 5 | 806.25
| 2" TRANSITION FITTING HDPE DR11 x 304SS MNPT | 49.57 | 5 | 247.85 |  | 5
| 2" COUPLING, S/F DR11 4710 | 2.46 | 10 | 24.6 |  | 10
| 4" X 2" BRANCH SADDLE, DR11 BF PE4710 ROUND BASE | 14.44 | 3 | 43.32 |  | 3
| 6" X 2" BRANCH SADDLE, DR11 BF PE4710 ROUND BASE | 14.44 | 1 | 14.44 |  | 1
| 8" X 2" BRANCH SADDLE, DR11 BF PE4710 ROUND BASE | 14.44 | 1 | 14.44 |  | 1
TVB-1521-6-G | OX,TORO VLV,15X21X6 RECT,GREEN | 57.6 | 5 | 288 |  | 5 |  | Invoice Recv'd/Cleared
TVB-1521EXT6BOX-G | OX,TORO VLV, 15X21X6EXT, GREEN | 69.3 | 5 | 346.5 |  | 5 |  | Invoice Recv'd/Cleared
| CHRISTY #IC.MAX.P2.RC006 RECLAIMED WATER TAG | 7.34 | 5 | 36.7
| DRAIN VALVES |  | 278.2
| 2" IPS DI GATE VALVE w/ DR11 PE ENDS & OP-NUT | 142.24 | 5 | 711.2 |  | 5
| 2" DR11 HDPE SOCKET FUSION ELBOW | 6.54 | 10 | 65.4
| 6" X 2" BRANCH SADDLE, DR11 BF PE4710 ROUND BASE | 14.44 | 3 | 43.32 |  | 3
| 8" X 2" BRANCH SADDLE, DR11 BF PE4710 ROUND BASE | 14.44 | 2 | 28.88 |  | 2
TVB-10RND-G | BOX,TORO VLV,10X10 ROUND,GREEN | 21.6 | 5 | 108 |  | 5
| NDS JUMBO RECTENGULAR VALVE BOX w/ NO LOCK LID, GREEN | 54.9 | 5 | 274.5
40F | CHRISTY #IC.MAX.P2.RC006 RECLAIMED WATER TAG | 7.34 | 10 | 73.4
| 8" ADS N-12 CORRUGATED PIPE (SLEEVE) | 8.63 | 10 | 86.3
0
*
| 2" ELECTRIC CONTROL VALVE |  | 545.23
P220G-27-08 | P220G 2" VALVE | 141.75 | 1 | 141.75 |  | 1 |  | Invoice Recv'd/Cleared
LSM-1 | LYNX SMART MODULE | 96.53 | 1 | 96.53 |  | 1
| 2" 90-ELL, S/F DR11 4710 | 6.54 | 1 | 6.54 |  | 1
| 2" COUPLING, S/F DR11 4710 | 2.46 | 1 | 2.46 |  | 1
| 2" X 2" TRANSITION FITTING HDPE DR11 x BRASS MNPT | 30.56 | 2 | 61.12 |  | 2
T-585 | 2" NIBCO BRASS BALL VALVE w/ SS HANDLE | 187.19 | 1 | 187.19
TVB-1217-12-G | BOX,TORO VLV,12X17X12 RECT,GREEN | 42.3 | 1 | 42.3 |  |  |  | Invoice Recv'd/Cleared
| CHRISTY #IC.MAX.P2.RC006 RECLAIMED WATER TAG | 7.34 | 1 | 7.34
| 1.5" ELECTRIC CONTROL VALVE |  | 506.47
P220G-27-06 | VALVE, P220G 1.5" | 108.99 | 1 | 108.99 |  | 1 |  | Invoice Recv'd/Cleared
LSM-1 | LYNX SMART MODULE | 96.53 | 1 | 96.53 |  | 1
AF1AS-218 | 1-1/2" AF INLET x 1" (12") BODY x 1" ACME STANDARD TOP OUTLET SJ | 65 | 1 | 65
T-585 | 1" NIBCO BRASS BALL VALVE w/ SS HANDLE | 54.98 | 1 | 54.98
AFAS150-020 | 2" X 1-1/2" AQUAFUSE SERVICE SADDLE | 29.76 | 1 | 29.76
| 2" X 1" TRANSITION FITTING HDPE DR11 x BRASS MNPT | 94.42 | 1 | 94.42 |  | 1
| 1" X 3" BRASS NIPPLE | 7.15 | 1 | 7.15
TVB-1217-12-G | BOX,TORO VLV,12X17X12 RECT,GREEN | 42.3 | 1 | 42.3
| CHRISTY #IC.MAX.P2.RC006 RECLAIMED WATER TAG | 7.34 | 1 | 7.34
0
*
2" | DR11 PE4710 HDPE FITTINGS, BUTT FUSION |  | 27635.64
1055 | 2 TEE | 9.78 | 600 | 5868 |  | 600
88 | 2 90-ELL | 7.78 | 300 | 2334 |  | 300
6" | DR11 PE4710 HDPE FITTINGS, BUTT FUSION
4 | 6 X 4 REDUCER | 36.89 | 5 | 184.45 |  | 5
8" | DR11 PE4710 HDPE FITTINGS, BUTT FUSION
5 | 8 TEE | 195.22 | 5 | 976.1 |  | 5
2 | 8 90-ELL | 135.33 | 2 | 270.66 |  | 2
21 | 8 45-ELL | 135.33 | 21 | 2841.93 |  | 21
3 | 8 X 6 REDUCER | 64.78 | 3 | 194.34 |  | 3
10" | DR11 PE4710 HDPE FITTINGS, BUTT FUSION
1 | 10 TEE | 456 | 1 | 456 |  | 1
2 | 10 X 8 REDUCER | 99.11 | 2 | 198.22 |  | 2
12" | DR11 PE4710 HDPE FITTINGS, BUTT FUSION
12 | 12 TEE | 646.67 | 1 | 646.67 |  | 1
9 | 12 X 10 REDUCER | 144.22 | 1 | 144.22 |  | 1
4 | 12 X 6 REDUCER | 131.11 | 1 | 131.11
14" | DR11 PE4710 HDPE FITTINGS, BUTT FUSION
1 | 14 X 10 REDUCER | 646.44 | 4 | 2585.76 |  | 4
1 | 14 X 12 REDUCER | 641.53 | 2 | 1283.06 |  | 2
2 | 14 TEE | 960.28 | 1 | 960.28 |  | 1
16" | DR11 PE4710 HDPE FITTINGS, BUTT FUSION
2 | 16 TEE | 1213.01 | 4 | 4852.04 |  | 4
1 | 16 90-ELL | 864.48 | 1 | 864.48 |  | 1
1 | 16 X 14 REDUCER | 711.08 | 4 | 2844.32 |  | 4
* |  |  |  | 0
| CENTRAL CONTROL, SMART HUBS & WS GROUNDING |  |  | 0
MIGPLATE96 | GROUNDING PLATE 4" X 96" | 200 | 2 | 400 |  | 2
TVB-1521-12 | TORO JUMBO RECTENGULAR VALVE BOX w/ LID, purple | 120 | 2 | 240 |  | 2 |  | Invoice Recv'd/Cleared
0
17.8 | SYSTEM GROUNDING |  |  | 0
DEC-SG | TORO DEC-SG SURGE PROTECTOR | 56.6 | 29 | 1641.4 |  | 29 |  | Invoice Recv'd/Cleared
GRPL4X96 | COPPER GROUND PLATE 4X96 W/25' 6 INS GRD | 195.4 | 29 | 5666.6 |  | 28 | missing 1
GR588 | 5/8 X 8 CU GROUND ROD | 34.48 | 29 | 999.92 |  | 29
CGT1161G-PLUS | CADWELD GT1161G - PLUS | 24.47 | 29 | 709.63 |  | 29
POWERSET50 | POWERSET - 50 LB. BAG | 114.94 | 29 | 3333.26 |  | 29
TVB-1217-12-G | BOX,TORO VLV,12X17X12 RECT,GREEN | 42.3 | 29 | 1226.7 |  | 29
0
| WIRE ACC |  |  | 0
| 3M 3570 G-N | 4.18 | 3000 | 12540 |  | 3000
| ELECTRICAL TAPE | 1.55 | 400 | 620 |  | 400
0
312BC | NDS 10" ROUND VALVE BOX w/ LID & COVER BOLT, GRAY | 25.61 | 15 | 384.15
| PAIGE WIRE TAGS | 37.26 | 20 | 745.2 |  | 20
MISCELLANEOUS
| 99% ISOPROPYL ALCOHOL 5 GAL. BOTTLE | 71.52 | 5 | 357.6 | Order from Rocky Mountain Reagants | 5 |  | Invoice Recv'd/Cleared
| MARKING PAINT, orange | 4.19 | 24 | 100.56 |  |  | Purchased on site
| DUCT TAPE | 6.51 | 12 | 78.12 |  |  | Purchased on site
1289 | FLAGS, white | 0.085 | 500 | 42.5 |  |  | Purchased on site
42 | FLAGS, pink | 0.085 | 300 | 25.5 |  |  | Purchased on site
29 | FLAGS, yellow | 0.085 | 200 | 17 |  |  | Purchased on site
#REF! | FLAGS, blue | 0.085 | 100 | 8.5 |  |  | Purchased on site
2 | FLAGS, orange | 0.085 | 100 | 8.5 |  |  | Purchased on site
| 4' GATE VALVE KEYS | 58.98 | 2 | 117.96
| 4' LATERAL ISOLATION VALVE KEYS | 9.44 | 2 | 18.88 |  | 2
| FILTER FABRIC | 92.5 | 4 | 370
0
REGENCY MAXI WIRE
83915 | 14-2 R7072D MAXI WIRE, HOT PINK | 0.3688 | 120000 | 44256 |  | 120000
118700 | SMART HUB TRUNK LINES |  |  | 0
13255 | 12-2 R7072D MAXI WIRE, RED | 0.544 | 8500 | 4624 |  | 8500
11590 | 12-2 R7072D MAXI WIRE, BLUE | 0.544 | 12500 | 6800 |  | 12000
| 12-2 R7072D MAXI WIRE, GREEN | 0.544 | 13500 | 7344 |  | 13500
0
scott oshiro
808 960 1684
tammi
casey